## CHECKLIST
NIKITA & SATHYA
Subject : Haldi, Sangeet & Wedding on 21&22nd November 2025 at Ramada, kochi
Sl No | Item & Description | Qty | Vendor | Check
COMMON LIGHTING & FLOATING DECOR
1 | Mirchi lights for 2 days | 1
2 | Green MH - 30no.s for 2 days | 1
3 | Pillar to pillar decor with Mariegold hangings and drapes | 10
4 | Event itinerary board | 1
21st Nov 2025 - HALDI (COURTYARD)
5 | Welcome board - Option 1 (as per design) | 1
6 | Petal station (petals on table) | 1
7 | Theme props with fresh flowers - Option 2 | 8
8 | Tender coconut cart with decoration | 1
9 | Tender coconuts *Rates can vary depends on season | 50
10 | Tree decor : Mariegold - 100pcs (10ft each) | 1
HALDI STAGE
11 | Haldi stage - Option 1 (as per design fresh & artificial flower mix) | 1
12 | Platform & platform masking with flex | 1
SEATING
13 | Tent - 10x10ft | 4
14 | Bench with cushion | 8
15 | Cylinder cushion seats | 16
16 | Chair Bow - Organza material | 30
ENTERTAINMENTS FOR HALDI
17 | Emcee | 1
18 | DJ (Ranges from 15k to 1L) | 1
19 | Platform for DJ (8X8ft) | 1
20th Nov 2025 - SANGEET (Royal Club)
20 | Welcome board - Option 1 (as per design) | 1
21 | Entrance arch with artificial flowers (Single arch) - Option 2 (as per design with) | 1
22 | Venue decor : Lanterns - Option 6 | 12
SANGEET STAGE
23 | Sangeet Stage without hangings - (24x12ft) - Option 8 | 1
24 | Platform masking with flex (24x12ft) | 1
25 | Couple couch with with artificial flower decor | 1
ENTERTAINMENTS FOR SANGEET
Emcee
26 | DJ (Ranges from 15k to 1L) | 1
27 | Platform for DJ - 8X8ft | 1
28 | Emcee | 1
LIGHT & SOUND SYSTEM FOR DAY 1
29 | Face lights | 8
30 | Sound system JBL /DB speaker tops main PA (4 no's)JBL /DB woofers for main PA(2 no's)Stage monitor's (2 no's)Mixer sound (1 no)Wireless handheld (2 no's)Package Rates Sound | 1
31 | DJ lights | 1
32 | Sharpy lights | 2
33 | Generator | 1
34 | Generator fuel rate will be at actual | 0
21st Nov 2025 - THALIKETTU (Pandhal)
35 | Welcome board - Option 1 | 1
36 | Entrance arch - Option 2 | 1
37 | Pathway carpet | 1
38 | Pathway decor stands | 12
39 | Theme props - Option 4 | 2
40 | Jasmine station (100 pieces) | 1
41 | White Cloth draping for pandhal (145x95sqft) | 1
42 | Green hangings for ceiling - | 1
WEDDING STAGE
43 | Wedding stage decor with mandapam 12x12ft - (with fresh & artificial flower hangings , as per design) | 1
44 | Platform & platform masking with flex (32x16ft) | 1
FLORALS
45 | Wedding Garlands - Lotus | 2
46 | Welcome garland | 1
47 | Welcome bouquet | 1
48 | Rose petal blast | 4
49 | Chaadar with fresh flower -Option 3 | 1
TRADITIONALS
50 | - Groom Welcome arrangement (Feet wash) - Orukk Items and arrangement Nilavilakku, Nirapara With Kathir And Pookula, Mixed Fruits Plate, Lemon Plates, Vettila Set ( Areca Leaf ) Thalam + Vilakku Set up. ( Each Thalam includes arecanut flower , rose petals , marriegold flower , small para , kasavu visari of cloth, small vilakku , nair wedding , the minimum number of thalam will be 11 + 1 as per the traditions, Thookuvilakk. | 1
51 | Nadaswaram (2 piece) | 1
52 | Platform for Nadaswaram (8x8ft) | 1
DECOR AT ROYAL CLUB
53 | Sadhya menu board with theme props | 1
54 | Entrance arch with fresh flowers and banana plants | 1
55 | Sadhya hall decor withy banana plants | 6
PHERA (Amphitheater lawn)
56 | Welcome Board | 1
57 | Entrance arch - Single arch | 1
58 | Walkway aisle with mirror sheet & flowering - 12X8ft | 1
59 | Stage decor - couple chairs. 4 low seats for parents, 1 low seater for pandit | 1
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2
Check Box 2

## Item LIST
Sl No | Item & Description | Qty
Day 1 : 29th November - Ring Exchange
1 | Welcome board with fresh flowers (as per design) | 1
A stand
Frame
Foam board
2 | Backdrop decor with fresh & artificial flowers, banana leaves - 16x10ft | 1
Frame
3 | Vedi chair for couple | 2
4 | Low seaters for parents & vadhyar | 6
| Cushion with cream cover | 4
5 | Platform masking with camel shade carpet - 24x12ft | 1
SHADES, FURNITURES FOR DAY 1
6 | Drapes for ceiling with off white cloth | 1
7 | Long tables | 10
8 | Round tables | 10
9 | Round table linen - white | 10
Cake stand, knife, tray
10 | Cart | 1
Camel shade carpet
11 | Long table linen (for breakfast & lunch) | 20
Day 2 : 30th Nov - WEDDING DECOR
15 | Welcome board with fresh flowers, Banana plants (as per design) | 1
Metal A stand
| Pathway stand | 10
| Uruli | 10
| Thalam | 10
Small Golden frame
16 | Entrance arch to pandhal - Artificial hangings with pink rose at tips ,banana plants(as per design) | 1
17 | Oonjal with decor (Fresh flowers & leaves) | 1
18 | Walkway decor (Fresh and artificial flowers & leaves) | 6
19 | Jasmine station and ganapathy orukk | 1
| Antique table | 1
Ganapathi
Jasmine - 50 piece
Hair slide
Kolam design pot
| Cane baskets | 2
WEDDING STAGE
20 | Wedding mandap pillar decor with artificial flowers, banana plants, leaves, hangings with artificial flowers and fresh flowers at tip, artificial flower props on floor (as per design) 10x10ft Palakai for couple | 1
Mandap frame
21 | Platform & covering with printed flex - 24x12 | 1
Steps
Mandapam
Kotta for draping

## PRODUCTION PLAN (3)
PRODUCTION PLAN
18 Nov, Tuesday
SL NO | ACTIVITY | START | FINISH | RESPONSIBLE
1 | Purchase Hamper items | 01.00 PM |  | ROHITH
2 | Collect Hamper bags from Sushil sir | 04.00 PM |  | ALFIYA
19 Nov, Wednesday
SL NO | ACTIVITY | START | FINISH | RESPONSIBLE
1 | Handover hampers to Ramada | 04.00 PM | 05.00PM | ALFIYA/ALFIYA
2 | Loading from Godown | 04.00 PM | 10.00PM | SUBIN/SAGAR
3 | Aravind - Transportaion | 04.00 PM | 10.00PM | ROHITH
4 | Ansar - Load Event itinerary board,flex,foam board,kotta | 04.00 PM | 10.00PM | ROHITH
20 Nov, Thursday
SL NO | ACTIVITY | START | FINISH | RESPONSIBLE
1 | At Ramada | 07.00AM | 10.00AM | SUBIN/ROHITH/SAGAR
1 | Subin Team 2 - Unloading & stacking (5ppl) | 07.00AM | 10.00AM | SUBIN
2 | Sabir - General lighting & Karaoke setup at Royal club | 07.00AM | 12.00PM | SABIR/ROHITH
3 | Hariz - Platform - Haldi, Sangeet, Thalikettu & Phera (ROUND) | 07.00AM | 02.00PM | HARIZ/ROHITH
4 | Joshy - Haldi tent, Pandhal tent (KOTTA & GREEN) | 07.00AM | 04.00PM | JOSHI/ROHITH
5 | Red rose from Ferin - 125NO.S | 07.00AM | 07.00AM | FIDA
6 | Ansar - Collect Rentals - Vattoly, festoon,plan b (Haldi & Sangeet) | 08.00AM | 12.00PM | ANSAR/ALFIYA
7 | Sagar - Event Itinerary (19th Nov may b) | 06.00AM | 09.00AM | SAGAR
8 | Subin Team 1 - General decor, stage, draping, hangings | 08.00AM | 01.00PM | SUBIN
9 | Sagar - WB,EA,PD, pool side decor, cart, petal station | 10.00AM | 01.00PM | SAGAR
10 | Subin Team 2 - The Dias | 10.30AM | 12.00PM | SUBIN
11 | Rest time | 01.00PM | 02.00PM | ROHITH
12 | Subin Team 2 - Stack items for Sangeet at Pandhal | 02.00PM | 05.00 PM | ROHITH
13 | Sabir - Sound check for Karaoke | 04.30 PM | 04.30 PM | FIDA
14 | James - projector & screen | 04.30 PM | 05.00 PM | ALFIYA
15 | Ansar - Flower from Aluva for Haldi,pooja & sangeet | 05.00 PM | 05.00 PM | ANSAR/FIDA
16 | Flower from coimbatore | 05.00 PM | 05.00 PM | ROHITH
17 | Handover Pooja items to sushil sir | 05.30 PM | 05.30 PM | ALFIYA
18 | Sagar & Subin - Fresh flowering | 06.00 PM | 06.00 PM | ROHITH
19 | Jaison - Food counter | 07.30 PM | 07.30 PM | ROHITH
21 | Subin Team 2 - cleaning at courtyard lawn | 09.30 PM | 10.30 PM | SUBIN
20 | Production at courtyard lawn complete | 10.00 PM | 10.00 PM | ROHITH
9 | Dinner & Rest | 10.30 PM | 21 Nov, 06.00 AM
10 | Subin Team 2 - Stack Sangeet items to Royal club | 12.00 AM
21 Nov, Fri
SL NO | ACTIVITY | START | FINISH | RESPONSIBLE
1 | Subin - Sangeet production at Royal club - Stage |  | 04.00 AM | ROHITH
2 | Subin Team 2 - Cleaning at Royal club
3 | Sagar - WB,EA,Photobooth,Table decor |  | 04.00 AM | SAGAR
4 | Promoters - petals | 07.00AM
5 | Sabir - Sound & light setup | 08.00AM |  | SABIR/FIDA
6 | Ansar - Tender coconut - | 07.00AM
7 | Ansar - Collect Rentals for 22nd Nov - Festoon,plan b | 08.00AM | 10.30AM | ALFIYA
8 | Subin Team 2 - Unloading & stacking Thalikettu & phera | 10.30AM | 01.00PM
9 | Production at poolside | 10.30AM | 03.30 PM | SUBIN
10 | Subin Team 2 - Dismantling at Courtyard lawn
11 | Sabir - Sound check at Royal oak | 05.00 PM
12 | DJ - Ricky | 05.30PM |  | FIDA
13 | Emcee - Mishti | 05.30PM
14 | Ansar - flower from Aluva for Thalikettu & phera | 06.30 PM |  | ANSAR/FIDA
15 | Ajish & Sagar - Flowering at pandhal | 06.30 PM
16 | Flower from coimbatore | 08.30 PM |  | ROHITH
17 | Subin team 2 - Dismantling at courtyard
18 | Subin - Production at Pandhal - Pathway,Mandap | 10.00 PM | 05.00AM | ROHITH
19 | Sagar - WB,EA,Jasmine station | 10.00 PM | 05.00AM
20 | Ajish & Sagar - Flowering at pandhal | 10.00 PM
22 Nov, Sat
SL NO | ACTIVITY | START | FINISH | RESPONSIBLE
1 | Subin Team 2 - Final cleaning at pandhal | 06.00AM | 07.00AM | ROHITH
2 | Ramachandran | 06.00AM
3 | Jeena - pookalam, Sadhya hall vaazha | 06.00AM
4 | Production at Pool side finish | 12.00PM
5

## PRODUCTION Manpower
RAMADA PRODUCTION
20th Nov - HALDI PRODUCTION
| SUBIN | SAGAR
1 | Subin Team 2 - Unloading & stacking (5ppl) | Sagar - Event Itinerary (19th Nov may b)
2 | Subin Team 1 - General decor, stage, draping, hangings | Sagar - Welcome board,Entrance arch, Pathway Decor
3 | Subin Team 2 - Decor at The Dias | Pool tree hanging decor, cart, petal station
4 | Subin Team 2 - Stack items for Sangeet at Pandhal | Sagar & Subin - Fresh flowering
5 | Subin Team 2 - cleaning at courtyard lawn | Ganapati decor
6 | Subin Team 2 - Stack Sangeet items to Royal club
7 | Subin & Sagar - Fresh flowering
20th Nov - SANGEET PRODUCTION
| SUBIN | SAGAR
1 | Subin - Sangeet production at Royal club - Stage | Sagar - WB,EA,Photobooth,Table decor
2 | Subin Team 2 - Cleaning at Royal club | Ganapati decor
3 | Subin Team 2 - Unloading & stacking Thalikettu & phera
4 | Subin Team 2 - Dismantling at Courtyard lawn
5 | Subin team 2 - Dismantling at courtyard
21st Nov - THALIKETTU PRODUCTION
| SUBIN | SAGAR
1 | Subin - Production at Pandhal - Pathway& carpet,Mandap | Sagar - WB,EA,Jasmine station,chaadar,olakuda
2 |  | Sagar & Ajish - Flowering at pandhal
Sadhya board
21st & 22 Nov - PHERA PRODUCTION
| SUBIN | SAGAR
1 | Subin Team 2 - Final cleaning at pandhal | Sagar - Pathway bouquets, Entrance arch, bridge decor
2 | Subin - Phera - Mandapam, Ramp | Seating arrangement, car bouquet,Ganapati decor

## GODOWN Item list
Ramada
Sl No | Item & Description | Qty
GODOWN - HALDI
1 | Wooden Elephant | 1
2 | Tassles - Yellow
3 | Tassles - Green, Orange
4 | Jute Bells YELLOW
5 | Rajasthani table for stage | 2
6 | Cushions | 10
7 | Dream catchers
8 | Itinerary board frame
9 | Tender coconut cart
10 | Knife
11 | Terracotta round pot
12 | Terracotta turtle & sun
13 | White flex
14 | Bluetooth speakers
15 | Console masking
GODOWN - SANGEET
1 | Glass tubes | 13
2 | Entrance arch
3 | Cushions | 4
4 | Backdrop arches | 5
5 | Backdrop frame
6 | Black cloth
7 | Off white tassles | 2
8 | Velvet cloth
9 | Oil, match box
10 | Tools
11 | Led candles
GODOWN - THALIKETTU
1 | Welcome board frame
2 | Bells
3 | Entrance arch frame
4 | Camel shade carpet
5 | Pathway stand big | 6
6 | Pathway stand small | 6
7 | Small golden frame
8 | Golden mirror
9 | Hair slide
10 | Bamboo baskets new | 6
11 | Thalam | 10
12 | Hangings- green leaf
13 | Paper prints from signtek
14 | Bamboo baskets for ceiling - kotta | 60
15 | Kasavu cloth
16 | Thalam | 10
17 | A stand
18 | Chaaadar
GODOWN - PHERA
1 | Entrance arch frame
2 | Mandap
3 | Round platform
4 | Lanterns
5 | Led Candles
6 | Car bouquet
7 | New round tray | 12
HALDI FLEX
1 | 1. Stage skirting - 18x2.5ft (1no.)
2 | 2. Dance floor - 20x12ft(1no.)
3 | 3. Dance floor skirting - 21x0.5ft(1no.)
4 | 4. Dance floor skirting - 20x0.5ft (2no.s)
5 | 5. Ramp - 20x8ft (1no)
6 | 6. Ramp skirting - 20x1½ft(2no.s)
7 | 7. Ramp skirting - 8x1½ft(1no)
8 | 8. Dj skirting - 8x0.5ft (3no.s)
9 | Welcome board - foam board
10 | Itineray board/flex
11 | Mandala art round - 1
12 | Itineray board/flex
13 | Mandala art round - 1
14 | Petal showe sticker - 1
15 | Petal showe sticker - 1
SANGEET - FLEX/FLEX
1 | Welcome board sticker
2 | 1. Sangeet floor - 32x16ft (1no)
3 | 2. Sangeet floor - 33x2ft (1no)
4 | 3. Sangeet floor - 16x2ft (2no)
5 | 4. Dj floor - 8x½ (3no.s)
THALIKETTU - FLEX/PRINTS
1 | 1. 32x20ft - 1no.
2 | 2. 33x1½ft - 1no.
3 | 3. 21x1½ft - 2no.s
4 | 4. 4ftx6inch - 2no.s
5 | Paper prints from signtek
6 | Welcome board foam board
PHERA - FLEX/PRINTS
1 | 1. 21x1½ft - 1no
2 | 2. 16x1½ft - 2no.s
3 | 3. 4ftx6inch - 2no.s
4 | Acrylic sheet

## RENTALS
PLAN B - Pickup
Sl No | Item & Description | Qty | Pickup | Drop
1 | Antique side table | 2 | 2025-11-29 | 2025-11-30
2 | Brass uruli | 16 | 2025-11-29 | 2025-11-30
3 | Brass vase small | 1 | 2025-11-28 | 2025-11-29
4 | Brass vessel | 2 | 2025-11-29 | 2025-11-30
5 | Wooden door with base/stand | 1 | 2025-11-28 | 2025-11-29
6 | Nilavilakk | 2 | 2025-11-28 | 2025-11-29
7 | Vedi chair | 2 | 2025-11-28 | 2025-11-29
8 | Choki | 6 | 2025-11-28 | 2025-11-29
9 | Amada petti | 1 | 2025-11-29 | 2025-11-30
10 | Antique table | 1 | 2025-11-29 | 2025-11-30
11 | Oonjal | 1 | 2025-11-29 | 2025-12-01
12 | Sofa - antique | 1 | 2025-11-28 | 2025-12-01
13 | Gopura kalasam | 4 | 2025-11-29 | 2025-11-30
14 | Cart | 1 | 2025-11-29 | 2025-11-30
15 | Ural | 1 | 2025-11-29 | 2025-11-30
17 | Carpet | 1 | 2025-11-29 | 2025-11-30
17 | Brass vessel | 4 | 2025-11-29 | 2025-11-30
18 | Brass bowl | 4 | 2025-11-29 | 2025-12-01
19 | Bharani | 2 | 2025-11-29 | 2025-11-30
20 | Single seater sofa | 6 | 2025-11-29 | 2025-11-30
21 | Cushion bench - off white | 4 | 2025-11-28 | 2025-11-29
22 | Bolster | 8 | 2025-11-28 | 2025-11-29
23 | Bolster cover - green |  | 2025-11-28 | 2025-11-29
24 | Stand | 1 | 2025-11-28 | 2025-11-29
25 | Garden umbrella - big with stand, base | 1 | 2025-11-30 | 2025-12-01
26 | Mirror table | 1 | 2025-11-29 | 2025-11-30
27 | Uruli big | 1 | 2025-11-29 | 2025-11-30

## PURCHASE
Ramada
Sl No | Item & Description | Qty
GODOWN
1 | Cane baskets - light pink,yellow,orange | 6
2 | Tender coconuts | 80
3 | Straw
4 | Tissue
5 | Garbage bag
6 | Red floating candles | 5
7 | Blue floating candles | 5
8 | White floating candles | 3
9 | Cushion cover | 4
10 | Cane basket for pandhal ceiling
13 | Ganapathi (7 inch) | 2
14 | Terracotta vase | 5
15 | Led floating candle | 40
16 | Black velvet cloth | 30 m
17 | Button battery | 1 packet
18 | Carpet (Camel shed) | 2 roll
19 | Bells (4 inch) | 30
20 | Golden spray paint | 1 box
21 | Artificial jasmine (2m) | 100 piece
22 | Orange marigold(1m) | 100 piece
23 | Lemon yellow laycra cloth | 48m
24 | Orange laycra cloth | 13 m
25 | Pink laycra cloth | 12 m
26 | Scissors | 10
27 | Cutting blade | 5
28 | Hair slide
30 | haldi paste
31 | Smokless cool fair | 1 box
32 | orange hanging ball | 10
YELLOW,PINK CLOTH

## PRINTS
PRINTS - BOLGATTY
Sl No | Item & Description | Qty
1 | Foam board cut out | 1
2 | Vinyl sticker | 1
3 | Vinyl mirror stcker | 1
4 | Platform flex - 24x12ft | 1
5 | Skirting flex - 25x1.5ft | 1
6 | Step - 5x2ft | 2
7 | Skirting flex - 13x1.5ft | 2
8 | 2x2ft vinyl sticker | 2
9 | 8x2ft vinyl sticker | 2
10 | 8x2ft vinyl sticker | 1
11 | 2x2ft vinyl sticker | 1
12 | 3x2ft foam board | 2